EduIG-Pipeline

Developer B — Task Guide

Your Personal Build Plan (Weeks 1–6)

| Version | 1.0 — 2026-05-31 |
| --- | --- |
| Role | Developer B (Your Friend) |
| Tool | Google Antigravity (Agent-First IDE) |
| Timeline | 6 Weeks (Part-time) |
| Your Tasks | Tasks 1, 2, 7, 8, 11, 14, 17 + shared tasks 12, 15, 18, 20, 21, 22 |

# 1. Your Role in the Project

You are Developer B. Your core strength is the infrastructure and integration layer — getting the project running, defining the data contracts (schemas), building the storage layer, and wiring everything together. You also own the optional Graph API worker and the final release process.

## Your Primary Ownership

| Week | Your Focus | Shared With Dev A |
| --- | --- | --- |
| Week 1 | Git setup (Task 1), Virtual Env & Dependencies (Task 2) | Review Dev A's config system & browser worker |
| Week 2 | Pydantic Schemas (Task 7), Router (Task 8), SQLite Storage (Task 11) | Connect pipeline in run.py (Task 12) |
| Week 3 | Error Handling & Resilience (Task 14) | Integration Tests (Task 15), compliance review |
| Week 4 | Graph API Worker (Task 17) | Jupyter Notebooks (Task 18) |
| Week 5 | CONTRIBUTING.md, Type hints review, Demo (Task 19 partial) | Final Verification (Task 20) |
| Week 6 | Methodology, Compliance audit, Presentation | End-to-End Test Run (Task 21), Compliance Report (Task 22) |

# 2. Your Git Setup Responsibilities

You set up the shared GitHub repository that both of you use. This is Task 1 and it's yours alone — do this on Day 1 of Week 1 before Dev A writes any code.

## Step 1: Create the GitHub Repository

- Create a new GitHub repository: EduIG-Pipeline (public or private — your team's choice)

- Add both yourself and Dev A as collaborators (Settings → Collaborators)

- Create branch protection rule on main: require PR reviews, no direct push

## Your Branches

Your Branches dev-b/week1-setup ¦ dev-b/week2-schemas ¦ dev-b/week2-router ¦ dev-b/week2-storage ¦ dev-b/week3-error-handling ¦ dev-b/week4-api-worker ¦ dev-b/week5-contributing

## Commit Format (Mandatory)

Every commit must follow this format — enforced by commitlint:

Format feat(scope): description [#task-number] Examples: feat(project): initialize repo with .gitignore and README skeleton [#1] feat(schemas): add ProfileSchema and PostSchema Pydantic v2 models [#7] feat(storage): implement SQLite WAL mode storage manager [#11] fix(router): handle missing OAuth token gracefully [#8]

# 3. Your Antigravity Setup (Do This Week 1, Day 1)

Set up Antigravity on your machine. Dev A is also setting up their workspace independently — you each have your own Antigravity environment.

## Step 1: Install & Create Workspace

- Download and install Antigravity from antigravity.google/download

- Sign in with your Google account

- Create new workspace named: EduIG-Pipeline

- Install the Chrome extension

## Step 2: Upload All 5 Project Documents

Create a docs/ folder in your workspace and upload all 5 files:

| # | File Name | Why You Need It |
| --- | --- | --- |
| 1 | PRD.md | Scope boundaries — check before every task to stay in scope |
| 2 | ARCHITECTURE.md | Module design and dependency graph — your storage and schema guide |
| 3 | AI_RULES.md | Non-negotiable coding rules — Antigravity MUST follow these |
| 4 | PLAN.md | Full task specs with deliverables and verification commands |
| 5 | PROMPT_FOR_ANTIGRAVITY.md | Exact prompts to paste into Antigravity for each of your tasks |

Tell Antigravity: "Read all documents in the docs/ folder before starting any work."

## Step 3: Copy 4 Skills Into Your Workspace

Terminal Commands cp -r /app/.agents/skills/web-scraper .agents/skills/ cp -r /app/.agents/skills/bash-scripting .agents/skills/ cp -r /app/.agents/skills/api-patterns .agents/skills/ cp -r /app/.agents/skills/workflow-automation .agents/skills/

## Step 4: Create Rule Files

Create .agents/rules/eduig-code-style.md with the content from PROMPT_FOR_ANTIGRAVITY.md Section 1.

Create .agents/rules/eduig-git-rules.md with the commit format rules.

## Step 5: Configure Permissions

- Allow list: command(git), command(python), command(pip), command(pytest), command(black), command(isort), command(mypy)

- Deny list: command(rm -rf), command(curl | sh)

# 4. How to Use Antigravity for Every Task

Follow this exact workflow for each task. Never skip Plan Mode.

| Step | Action | Details |
| --- | --- | --- |
| 1 | Read the task | Read your task section in PLAN.md + the matching prompt in PROMPT_FOR_ANTIGRAVITY.md |
| 2 | Open Antigravity | Start in Plan Mode — NOT Code Mode yet |
| 3 | Paste the prompt | Copy the exact prompt from PROMPT_FOR_ANTIGRAVITY.md Section 3 for your task |
| 4 | Review the plan | Read Antigravity's implementation plan. Add requirements if anything is missing. Check AI_RULES.md |
| 5 | Approve → Code Mode | Once plan looks right, approve it and switch to Code Mode |
| 6 | Monitor progress | Watch artifacts appear. Ask for corrections if wrong |
| 7 | Run tests locally | Run: pytest tests/test_<module>.py -v — do not trust agent's self-report |
| 8 | Check coverage | Run: pytest --cov=src.<module> --cov-fail-under=80 |
| 9 | Type check | Run: mypy src/<module>.py --strict |
| 10 | Format check | Run: black --check src/<module>.py && isort --check-only src/<module>.py |
| 11 | Commit & PR | Commit with proper format. Create PR for Dev A to review. |

Golden Rule NEVER skip Plan Mode review. If tests fail after Antigravity says 'Done', paste the exact error back and say: 'Fix this test failure. Do not change unrelated code.'

# 5. Your Task Details (Week by Week)

## WEEK 1 — Foundation

Goal: Set up the shared Git repository, Python environment, and project structure. Dev A depends on your setup being ready before they write any code.

### Task 1: Initialize Project Structure

| Priority | P0 — Everything depends on this |
| --- | --- |
| Depends on | Nothing — you start here |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 1 → Task 1.1 |
| Your branch | dev-b/week1-setup (this is your first commit) |

What Antigravity must build for you:

- Complete directory structure per ARCHITECTURE.md Section 5.1 (all folders and empty __init__.py files)

- Git repository initialized with .gitignore excluding: venv/, data/, .env, __pycache__/, *.pyc, .pytest_cache/, .DS_Store

- LICENSE file — MIT license for academic use

- README.md skeleton with all section headers (Overview, Install, Configure, Run, Test, Compliance, Citation, License)

- .env.example template with all required variable names

- First commit: feat(project): initialize EduIG-Pipeline repository [#1]

Verify Task 1 git status # Should be clean tree -L 3 # Should show full structure per ARCHITECTURE.md

### Task 2: Virtual Environment & Dependencies

| Priority | P0 — Dev A can't install anything without this |
| --- | --- |
| Depends on | Task 1 |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 1 → Task 1.2 |
| Your branch | dev-b/week1-setup (continue on same branch) |

What Antigravity must build for you:

- requirements.txt with ALL pinned versions (see PLAN.md Task 2 for exact list)

- scripts/setup.sh — checks Python ≥3.10, creates venv, upgrades pip, installs requirements, runs playwright install chromium, runs health check

- scripts/health_check.py — verifies all imports work (playwright, httpx, pydantic, structlog, pandas, polars, yaml)

- Makefile with targets: install, test, lint, format, run, health-check

Verify Task 2 make install make health-check python -c "import playwright, httpx, pydantic, structlog, pandas"

IMPORTANT Once Tasks 1 and 2 are done and pushed, tell Dev A: 'Repo is ready. Clone and run make install.' They cannot start until this is done.

## WEEK 2 — Core Pipeline

Goal: Define all data schemas, build the router, and create the storage layer. These are the backbone modules that everything else connects to.

### Task 7: Pydantic Schemas

| Priority | P0 — All modules import schemas from this file |
| --- | --- |
| Depends on | Task 6 (Rate Limiter — Dev A must finish first) |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 2 → Task 2.3 |
| Your branch | dev-b/week2-schemas |

What Antigravity must build for you:

- src/schemas.py — all 5 Pydantic v2 models

- ProfileSchema — profile_id (hashed), username_hash, bio (str | None), followers, following, posts_count, extracted_at, source: Literal['api','browser']

- PostSchema — post_id, profile_id, caption, likes, comments, hashtags: list[str], posted_at, engagement_rate

- RunSchema — run_id, started_at, completed_at, targets_count, success_count, failure_count

- AuditLogSchema — timestamp, run_id, target, action, status: Literal['success','failure','skipped'], bytes_collected, compliance_note, error_message

- TargetSchema — username, url, consent_status: Literal['granted','denied','pending','public_only'], notes

- All models: model_config = ConfigDict(strict=False), to_json() method, from_json() classmethod

- Custom validators: bio truncated to 500 chars, whitespace stripped

- tests/test_schemas.py — validation tests, serialization tests, ≥80% coverage

Verify Task 7 pytest tests/test_schemas.py -v --cov=src.schemas --cov-fail-under=80

IMPORTANT After merging this PR, tell Dev A immediately — they need schemas.py for Tasks 9 and 10.

### Task 8: Router

| Priority | P0 — Decides which worker handles each target |
| --- | --- |
| Depends on | Task 7 |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 2 → Task 2.2 |
| Your branch | dev-b/week2-router |

What Antigravity must build for you:

- src/router.py — Router class with route(target: TargetSchema) → Worker decision logic

- Decision matrix: Valid OAuth + consent granted → API Worker; public profile, no OAuth → Browser Worker; private, no auth → skip + log

- has_valid_oauth() → bool: checks env var INSTAGRAM_ACCESS_TOKEN

- Every routing decision logged to audit log

- tests/test_router.py — all 4 routing paths tested with mocked workers, ≥80% coverage

Verify Task 8 pytest tests/test_router.py -v --cov=src.router --cov-fail-under=80

### Task 11: SQLite Storage

| Priority | P0 — All data persistence goes through this module |
| --- | --- |
| Depends on | Task 10 (Normalizer — Dev A must finish first) |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 2 → Task 2.6 |
| Your branch | dev-b/week2-storage |

What Antigravity must build for you:

- src/storage.py — StorageManager class

- WAL mode on every connection: PRAGMA journal_mode = WAL; PRAGMA foreign_keys = ON; PRAGMA synchronous = NORMAL

- 4 tables: profiles, posts, runs, audit_log (see PLAN.md Task 11 for exact schema)

- Methods: save_profile(), save_posts(), save_run(), save_audit_log(), get_profile(), export_to_csv(), export_to_json(), check_duplicate(), close()

- Context manager support (with StorageManager() as s:)

- Atomic transactions — all writes inside try/except with rollback

- tests/test_storage.py — integration tests with in-memory SQLite (:memory:), ≥80% coverage

Verify Task 11 pytest tests/test_storage.py -v --cov=src.storage --cov-fail-under=80 python -c "from src.storage import StorageManager; s = StorageManager(':memory:'); print('Storage ready')"

### Task 12: Main Orchestrator — run.py (SHARED WITH DEV A)

This task requires both of you to coordinate. You focus on CLI args, storage calls, and the run lifecycle. Dev A focuses on the target processing loop (rate limiter, parser, normalizer).

Coordination Point Meet with Dev A when both Tasks 11 and 10 are done. Decide: will one person write run.py and the other reviews, or will you divide the function by area? Recommended: you write the skeleton (CLI, init, cleanup) and Dev A fills in the processing loop.

## WEEK 3 — Compliance & Robustness

Goal: Error handling and resume logic — making the pipeline production-grade.

### Task 14: Error Handling & Resilience

| Priority | P0 — Pipeline must never crash and lose data |
| --- | --- |
| Depends on | Task 13 (Dev A's compliance module) |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 3 → Task 3.2 |
| Your branch | dev-b/week3-error-handling |

What Antigravity must build for you:

- Enhance all workers: try/except/finally around ALL external calls

- Graceful degradation: save partial data on failure (don't discard what was collected)

- Resume capability: save run state to SQLite after each target; track last successful target index

- Resume logic: python run.py --resume run_001 — skips already-completed targets

- Dry-run mode: python run.py --dry-run — validates config and targets without any network calls

- Update run.py: keyboard interrupt handling (Ctrl+C saves state and closes browser gracefully)

- atexit hooks for unexpected process termination

- tests/test_resilience.py — simulate network failure mid-run, verify state saved, verify resume works

Verify Task 14 pytest tests/test_resilience.py -v python run.py --dry-run # Should complete without errors python run.py --resume run_001 # Test actual resume (after a real interrupted run)

### Task 15: Integration Tests (SHARED WITH DEV A)

Both of you write integration tests together in Week 3 Day 3–4. Your focus: test error handling paths — network failure simulation, state saving, resume logic, consent checking.

## WEEK 4 — Advanced Features

### Task 17: Graph API Worker

| Priority | P1 — Optional feature (pipeline works without it) |
| --- | --- |
| Depends on | Tasks 13, 15, 16 |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 4 → Task 4.2 |
| Your branch | dev-b/week4-api-worker |

What Antigravity must build for you:

- src/api_worker.py — APIWorker class with httpx.AsyncClient

- OAuth 2.0 token management: reads INSTAGRAM_ACCESS_TOKEN env var, token refresh logic

- _get_headers() → dict: Bearer token header

- get_user_profile(user_id) → dict: calls /{user-id} endpoint

- get_user_media(user_id, limit=10) → list[dict]: calls /{user-id}/media

- get_media_insights(media_id) → dict: calls /{media-id}/insights

- Error handling: token expiry, permission errors, quota exceeded (all logged + graceful)

- Only activates when OAuth token present AND consent_status == 'granted'

- tests/test_api_worker.py — mocked httpx tests, ≥80% coverage

- Document clearly: this is OPTIONAL — pipeline works 100% without it

Verify Task 17 pytest tests/test_api_worker.py -v --cov=src.api_worker --cov-fail-under=80

### Task 18: Jupyter Notebooks (SHARED WITH DEV A)

Both of you create the 3 analysis notebooks together. Your focus is notebook 02 (Engagement Metrics) — engagement rate distribution, correlation analysis, hashtag frequency, visualizations.

## WEEK 5 — Polish & Documentation

### Task 19 (Your Part): CONTRIBUTING.md & Type Hints

| Priority | P0 — Required for team coordination |
| --- | --- |
| Depends on | Task 18 |
| Prompt to use | PROMPT_FOR_ANTIGRAVITY.md → Phase 5 → Task 5.1 |
| Your branch | dev-b/week5-contributing |

What Antigravity must build for you:

- CONTRIBUTING.md — branch strategy (dev-a/feature-name, dev-b/feature-name), commit format, PR process, code review checklist

- Review all src/ files for missing type hints — ask Antigravity to add type hints to any untyped functions

- Create a short demo script or README section showing the pipeline running end-to-end

- .pre-commit-config.yaml — hooks for black, isort, flake8, mypy, pytest (fast subset), git-secrets

### Task 20: Final Verification (SHARED WITH DEV A)

### Task 21: End-to-End Test Run (SHARED WITH DEV A)

### Task 22: Compliance Report & Release (SHARED WITH DEV A)

These three final tasks are done together. See the Shared Tasks section at the end of this document.

# 6. Your Per-Task Quality Checklist

Before you create a PR for every task you complete, run through this checklist:

| ☐ | Check | Command |
| --- | --- | --- |
| ☐ | Tests pass | pytest tests/test_<module>.py -v |
| ☐ | Coverage ≥80% | pytest --cov=src.<module> --cov-fail-under=80 |
| ☐ | Type check passes | mypy src/<module>.py --strict |
| ☐ | Formatting clean | black --check src/<module>.py |
| ☐ | Import order clean | isort --check-only src/<module>.py |
| ☐ | No print() statements | grep -n 'print(' src/<module>.py # Must return nothing |
| ☐ | No credentials in code | git-secrets --scan |
| ☐ | No Optional[] usage | grep -n 'Optional\[' src/<module>.py # Must return nothing |
| ☐ | WAL mode in storage calls | Grep: PRAGMA journal_mode = WAL present in storage.py |
| ☐ | Docstrings on all public methods | pydoc src.<module> |
| ☐ | Commit message format correct | feat(scope): description [#N] |

# 7. Shared Tasks (Do These With Developer A)

These tasks require both of you to coordinate. Use your daily check-in to stay in sync.

| Task | Week | Your Contribution | Dev A's Contribution |
| --- | --- | --- | --- |
| 12 | Week 2 | CLI args, storage calls, run lifecycle (init/cleanup) | Rate limiter + parser + normalizer loop integration |
| 15 | Week 3 | Error handling tests, resume logic tests | Pipeline data flow tests, compliance tests |
| 18 | Week 4 | Notebook 02 (Engagement Metrics + visualizations) | Notebooks 01 and 03 (Exploratory + Compliance) |
| 20 | Week 5 | Run coverage + lint checks across your modules | Run coverage + lint checks across Dev A's modules |
| 21 | Week 6 | Create test targets.csv, set up 10-profile test run | Monitor run, verify data quality in SQLite |
| 22 | Week 6 | Generate CHANGELOG, tag v1.0 release, clean repo | Verify compliance report, write PROJECT_SUMMARY.md |

# 8. Dependency Coordination With Dev A

Your modules and Dev A's modules depend on each other. Track these handoff points carefully.

| When | You Need From Dev A | Dev A Needs From You | Action |
| --- | --- | --- | --- |
| Before Task 7 | Task 6 merged (rate_limiter.py) | Tasks 1+2 merged (repo + venv) | Sync on Day 1 of Week 2 |
| Before Task 11 | Task 10 merged (normalizer.py) | Task 7 merged (schemas.py) | Sync mid-Week 2 |
| Task 12 (run.py) | Tasks 6, 9, 10 merged | Tasks 7, 8, 11 merged | Meet at end of Week 2 |
| Task 14 | Task 13 merged (compliance.py) | Task 14 needed for final testing | Sync start of Week 3 |
| Task 17 | Tasks 15, 16 merged | Task 17 optional but good to review | Sync start of Week 4 |

# 9. Troubleshooting & Recovery

| Problem | What To Do |
| --- | --- |
| Antigravity generates raw dict passing instead of Pydantic models | Stop. Reference AI_RULES Rule 2. Ask agent: 'Replace raw dict returns with the appropriate Pydantic BaseModel' |
| Storage module uses PostgreSQL instead of SQLite | Stop. Reference AI_RULES Rule 5. Reject entirely — ask for SQLite with WAL mode |
| Schemas use Optional[str] instead of str ¦ None | Stop. Reference AI_RULES Rule 1. Ask: 'Replace all Optional[x] with x ¦ None syntax' |
| Router doesn't log routing decisions | Reference ARCHITECTURE.md Section 2.3. Ask: 'Every routing decision must be logged to the audit log' |
| Storage doesn't have WAL mode | Reference AI_RULES Rule 5. Ask: 'Add PRAGMA journal_mode = WAL to every connection initialization' |
| Error handling catches exceptions but doesn't log them | Ask: 'All caught exceptions must call logger.error() with the full exception context' |
| Dev A's task is blocking your task | Check if you can build with mock imports first. Communicate via check-in. Don't block — build what you can. |

# 10. Phase Gate Checklists

Both Dev A and Dev B must agree before moving to the next phase.

## Gate 1: Foundation → Core Pipeline (after Week 1)

- GitHub repo created, both collaborators added

- All dependencies install successfully: make install

- Health check passes: make health-check

- Dev A can extract 1 real profile successfully

- Logger writes JSON to file

## Gate 2: Core Pipeline → Compliance (after Week 2)

- All Pydantic schemas pass validation tests

- Router correctly decides between API and Browser worker

- SQLite storage saves and retrieves all data types

- Full pipeline runs on 5 targets: python run.py

- All Tasks 7, 8, 11 tests passing at ≥80% coverage

## Gate 3: Compliance → Advanced (after Week 3)

- Pipeline resumes correctly after interruption

- Dry-run mode works: python run.py --dry-run

- Integration tests pass for all error paths

- Circuit breaker opens and closes correctly

# 11. Task 22 — Release Duties (Yours)

You are responsible for the final release mechanics. Dev A handles the compliance report content, you handle the Git release.

- Generate CHANGELOG.md — list all 22 tasks with completion dates

- Tag the release: git tag -a v1.0 -m "EduIG-Pipeline v1.0 - MVP Release"

- Verify .env is in .gitignore and NOT in the repository

- Verify data/ is in .gitignore and NOT in the repository

- Delete any test profiles or personal data from the repo

- Run final git status — must be completely clean

- Push the tag: git push origin v1.0

Final Release Command git status # Must be clean git tag -l # Must show v1.0 git log --oneline # Must show all task commits with proper format

# 12. Quick Reference

| Reference | Location |
| --- | --- |
| Your task prompts | PROMPT_FOR_ANTIGRAVITY.md → Section 3 (Task 1.1, 1.2, 2.2, 2.3, 2.6, 3.2, 4.2, 5.1) |
| Full task specs | PLAN.md → Tasks 1, 2, 7, 8, 11, 14, 17 |
| Module design | ARCHITECTURE.md → Section 2 (especially 2.5 for storage schema) |
| Coding rules | AI_RULES.md — read before every PR review |
| Feature scope | PRD.md → Section 3 (features) and Section 6 (out of scope) |
| Dev A's tasks | See DEVELOPER_A_TASKS.docx |
| Daily check-in | 5-minute Discord/Slack sync every day |
| Weekly sync | Video call every Sunday — review progress, plan next week |

Remember You are the infrastructure lead. Dev A builds on top of what you create. Get Tasks 1 and 2 done first and fast — they unblock everything.